## Gantt Chart Template
|  | Milestone 1 (Project Initiation) |  |  | Milestone 2 (Project Development) |  |  | Milestone 3 (Project Evaluation & Submission)
TASK TITLE | COMPLETION | Week 4 & 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13
Constructing Ideas
Individual Brainstorming | 100% | [8 empty] | Rerved for Final Polish Before Submission
Team Discussion | 100%
Idea Selection | 100%
Sponsor Idea Review | 100%
Idea Tweaking | 100%
Second Sponsor Idea Review | 100%
Creative Concept | 100%
Final Idea Adjustments | 100%
Design
Write Music Theme | 0%
Star/Orb 3D Model | 0%
Tree Assets | 0%
Flower Assets | 0%
Skybox Stages | 0%
Skybox Final Look | 0%
Star Shaders - Glow Effect | 0%
Orb Grouping Behaviour | 0%
Orb Spawning Plan | 0%
Oustanding Design Elements | 0%
Development
Environmental Audio | 0%
Environment Aesthetics | 0%
Orb Handling Mechanic | 0%
Orb Spawning Mechanic | 0%
Orb Movement Algortihm | 0%
Orb Flocking Algorithm | 0%
Oustanding Dev Elements
Evaluation
Project QA | 0%
Bug Fixing / Polish | 0%
Documentation
Deliverable 2 | 0%
Deliverable 3 | 0%
Deliverable 4 | 0%
Deliverable 5 | 0%
Deliverable 6 | 0%