## Gantt Chart Template
|  |  | Milestone 1 (Project Initiation) |  |  | Milestone 2 (Project Development) |  |  | Milestone 3 (Project Evaluation & Submission)
TASK TITLE | TEAM MEMBER | COMPLETION | Week 4 & 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13
Constructing Ideas
Individual Brainstorming | Group | 100% | [8 empty] | Rerved for Final Polish Before Submission
Team Discussion | Group | 100%
Idea Selection | Group | 100%
Sponsor Idea Review | Group | 100%
Idea Tweaking | Group | 100%
Second Sponsor Idea Review | Group | 100%
Creative Concept | Group | 100%
Final Idea Adjustments | Group | 100%
Design
Write Music Theme | Greta | 80%
Star/Orb 3D Model | Tyla | 100%
Tree Assets | Tyla | 100%
Flower Assets | Tyla | 0%
Skybox Stages | Greta | 0%
Skybox Final Look | Greta | 0%
Star Shaders - Glow Effect | Greta | 0%
Orb Grouping Behaviour | Edgar | 20%
Orb Spawning Plan | Edgar | 0%
Oustanding Design Elements | Sam | 0%
Development
Environmental Audio | Greta | %
Environment Aesthetics | Tyla | 100%
Orb Handling Mechanic | Sam | 25%
Orb Spawning Mechanic | Edgar | 75%
Orb Movement Algortihm | Edgar | 80%
Orb Flocking Algorithm | Edgar | 10%
Oustanding Dev Elements | Sam
Evaluation
Project QA | Patrice | 0%
Bug Fixing / Polish | Patrice | 0%
Documentation
Deliverable 2 | Group | 0%
Deliverable 3 | Group | 0%
Deliverable 4 | Group | 0%
Deliverable 5 | Group | 0%
Deliverable 6 | Group | 0%